## Slide 1: En Route Controller Pilot Data Link Communications (CPDLC) Status Overview
Son Tran
Federal Aviation Administration
September 29, 1999

## Slide 2: Contents
FAA/Industry efforts to define CPDLC path
CPDLC implementation approach
  CPDLC Build I
  CPDLC Build IA
System architecture
Schedule interdependencies
Systems Integration and Program Coordination
FAA ground software development approach
PETAL II support
Programs and Baselines
Human Factors/FAA Test Bed Activities
Operational Safety Assessment -- Build I & IA
Risks Assessments & Accomplishments

## Slide 3: JOHN KERN DATA LINK ISSUES TEAM
The team recommended using the following phase approach for developing and implementing ICAO’s standard En Route Aeronautical Telecommunication Network (ATN) compliant data link services:
  Build I (domestic CPDLC)
    Four ATN compliant operational services
    Use VHF Digital Link Mode 2 (VDL-2) as A/G Sub-network
  Build IA (enhanced domestic CPDLC)
    ATN compliant services (increase message set for Acknowledgement, Speed, Heading, Route)
    Use VDL-2 as A/G Sub-network
  Build II (international CPDLC)
    ATN compliant services (more complex messages and downlinks)
    Use VDL-2 as A/G Sub-network
  Build III
    ATN message set
    Integration with Decision Support Systems
    Use Next Generation Air/Ground Communications (NEXCOM) as A/G
    Sub-network

## Slide 4
En Route
Controller Pilot Data Link Communications
Implementation Path
CPDLC II
CPDLC I
CPDLC IA
2001
2002
2003
2004
2005
2006
2011 +
2007 -10
Avionics
CPDLC III
CPDLC I
CPDLC IA
CPDLC II
Keysite
Keysite
National
Deployment
National
Deployment
Ground
CPDLC III
Keysite
Note: CPDLC II and CPDLC III are not baselined
NEXCOM Analog Voice
NEXCOM Digital Voice
A/G
Subnetwork
NEXCOM Digital Data
VDL-2

## Slide 5: FAA JOINT RESOURCE COUNCIL INVESTMENT DECISION
JRC Investment Decision on 10/30/98
  En Route CPDLC Build I (key site only)
  En Route CPDLC Build IA (national deployment)
Additional Investment Decisions required prior to beginning Builds II & III
  En route CPDLC Build II JRC Investment Decision is currently scheduled for Fall 2000

## Slide 6: EN ROUTE CONTROLLER PILOT DATA LINK COMMUNICATIONS BUILD I SUMMARY
    Single-site deployment
      Key site: Miami Air Route Traffic Control Center (ARTCC)
      Key site Initial Operational Capability (IOC): 6/02
    Provides 4 operational services
      Transfer of Communication
      Initial Contact
      Altimeter Setting
      Informational free text menu capability built by supervisor inputs
    Uses VDL-2 as A/G subnetwork
    Includes Human Factors demonstration at FAA Tech Center by 12/00
    American Airlines will be the launch airline

## Slide 7
    National deployment to all
    20 domestic ARTCCs
      Key site IOC: 6/03 Miami
      National deployment
        Begin installation: 1/04
        Complete installation: 12/04
EN ROUTE CONTROLLER PILOT DATA LINK COMMUNICATIONS BUILD IA SUMMARY
    Increase the message set to accommodate assignment of speeds, headings, altitudes as well as a route clearance function
    A capability to handle pilot-initiated altitude requests
    Uses VDL-2 as A/G Sub-network
    Anticipate widespread industry participation

## Slide 8: En Route CPDLC Architecture
VDL-2 Ground
Stations
CMU/ATSU ATN compliant
VDR Multi-Mode
Transceivers
DLAP
HOST
Router
DSR
NAS LAN
HID
CMA
NSM
FAA En Route CPDLC Ground System
G/G ATN
Router
MPS
ATN Network
Manager
NEXCOM VDL-3 Ground Stations
G/G ATN
Router
A/G ATN
Router
VDL-2 CPDLC I, IA, & II
ARTCCs/Subnetwork
Service Providers/CAAs
A/G ATN
Router
Ground Network Interface (GNI)
Display
NADIN II

## Slide 9
En Route CPDLC - Build I
Schedule Interdependencies
12/98
12/99
12/00
12/01
Host
6/02 - IOC
Controller
Miami ARTCC
ARINC
Operational
VDL-2/ATN A/G
Subnetwork
American Airlines CPDLC
ATN Aircraft
VDL-2/ATN
A/G Subnetwork
Internal Interdependency
External Interdependency
Completed
Production
DLAP System
Host A5f1.2
Release
DSR
G/G ATN
Router
ATNSI/ACI
ATN SW
HID/NAS
LAN
Rockwell
ATN CMU
Rockwell
VDL-2 VDR
CPDLC/HOST S/W
ProATN V2.2 Demo
PETALII
Trials

## Slide 10: Systems Integration and Program Coordination
CPDLC Integration Team (CIT) formed to meet monthly
  Comprised of FAA, ACI, ARINC, Rockwell-Collins, American Airlines, ATNSI, MITRE, Boeing (invited)
  Each organization presents their program status, major milestone schedule and progress, and program risks based on earned value
  CIT addresses and resolves technical and programmatic issues
Main Products
  Technical and programmatic risk table with mitigation
  Integrated schedule
  CPDLC Network Analysis

## Slide 11: FAA ATN Ground/Ground Router Development Approach
ATN Ground-to-Ground (G/G) router being managed by Telecommunications Integrated Product Team (TIPT)
Goal is to have ATN G/G router infrastructure in Miami ARTCC for operational implementation in June 2002
Will participate in the FAA/Japanese Civil Aviation Bureau (JCAB) trial in Spring 2000
Focus on Aeronautical Fixed Telecommunications Network (AFTN)/ATN Message Handling Service (AMHS) using ATN G/G router to exchange data

## Slide 12: FAA ATN Ground/Ground Router Development Approach (cont.)
FAA Tech Center will assist in G/G ATN router interoperability testing
ATN documentation developed and under review
  Router Architecture and Addressing Plan
  Router Requirements Document
  Router Test Plan and Procedures
  AMHS Integration Plan

## Slide 13: Host Software Development Risk Mitigation
Use ProATN HW/SW platform as a “black box” with FAA DLAP to support Host software development and Host software Operational Test and Evaluation (OT&E)
  Eliminates Host software dependency on final ATNSI RRI and ACI ASE software
  Provides necessary requirements/development stability to meet Host software development/integration schedule

## Slide 14: DLAP Software Development Strategy
DLAP software consists of two separate development activities
  ProATN DLAP
    Supports Host development, OT&E, and Host integration schedules
  Production DLAP
    Supports production-level DLAP at Miami Center
    Development schedule is dependent on the availability of ATNSI RRI and ACI ASE software
    Requires DLAP OT&E and system regression testing

## Slide 15: CPDLC I & IA Contracts & Software Development
CPDLC I requirements analysis is complete
CPDLC I Critical Design Review (CDR) is scheduled for 11/99
CPDLC/ProATN demo is scheduled for 11/99
Screening Information Release (SIR) for CPDLC IA contract was released on 9/3/99; contract award planned for 2/00

## Slide 16: PETAL II Support
Agreed to PETAL II extension (PIIe) message set which includes CPDLC I and CPDLC IA messages
Participated in the PETAL II Interoperability Team (PIT) meetings to identify and resolve differences between PETAL II and U.S. implementations
Participated in the development of the PETAL II Trials End-to-End Specification - the specification is baselined
Minimized change to avionics implementation and aircrew procedures
Continue to participate in PIT to:
  Address and resolve ICAO ATN SARPs and PETAL IIe trials specification defect reports
  Develop detailed plan on the VDL-2/ATN interoperability testing
  Refine the planning for transatlantic certification and safety work

## Slide 17: Programs and Baselines
Baseline One
ICAO Doc 9705 (ATN) RTCA/Eurocae 1
P-II Spec’s v.3
PETAL-II extension
FAA Builds I & IA
Baseline Two
ICAO Doc 9705 (ATN) RTCA/Eurocae 2
Link2000+ Spec’s
Link2000+
FAA Build II
Notes: <number>
<footer>
<header>
<date/time>

## Slide 18: Baseline Development
FAA Program
RTCA
EUROCAE
RTCA
EUROCAE
PIT
B2T
PROPOSED
BASELINES
Baseline
2
Baseline
1
LINK2000+
INTERNATIONAL
BASELINES
REQUIRE
DEVELOP
baseline
ENDORSE
IMPLEMENT
Notes: <number>
<footer>
<header>
<date/time>

## Slide 19: Human Factors/FAA Test Bed Activities
Continued effort to identify the CPDLC Human Factors and the FAA Test bed activities to be completed in CY00 leading up 12/00 Human Factors demonstration
Ground HCI/Procedures/Training Evaluation, Sept 1999 for Builds I and IA HCI
Flight Deck HCI study, Oct 1999 which compared alternative configurations (EICAS, Glareshield, and MCDU only) dedicated and shared displays

## Slide 20: Planned Human Factors Activities
Proposed
  Initial ATSS/Pilot/System Integration Test and Evaluation, March 2000
    Focus on Controller/Pilot Procedures in Nonpositive situations
    Focus on Flight Crew and Sector Team Coordination
  Second ATSS/Pilot/System Integration Test and Evaluation, July 2000
    Dry Run of Protocols for Human Factors Demonstration
    Focus on Flight Deck Task Integration: CPDLC/FMS Tasks
  ATSS/Pilot/System Integration Demonstration
Goal: Demonstrate Effectiveness & Acceptability of CPDLC human factors elements
  messages/information requirements
  HCI
  procedures and training
  operational performance

## Slide 21: Test Configuration Summary

## Slide 22: FAA Test Strategy

## Slide 23: Operational Safety Assessment (OSA) Accomplishments--Build I
Completed Draft Operational Environment Description (OED) for Build I Feb 12, 1999
Completed Operational Hazard Assessment (OHA) for Build I April 16, 1999
Completed Allocation of Safety Objectives and Requirements (ASOR) For Build I May 3, 1999

## Slide 24: Operational Safety Assessment (OSA) Accomplishments--Build IA
Completed Draft OED for Build IA/Baseline I May 15, 1999
Completed OHA for Build IA/Baseline I June 11, 1999
Completed first draft of Safety and Performance Requirements (SPR) July 14, 1999
Completed first draft Of SC-189 PUB26 document. July 14, 1999

## Slide 25
ICAO Standards ATN & VDL-2 SARPs
Certification
Plan
SC-189 / WG-53
Subgroup 1
Baseline 1
Interoperability Document
Subgroup 2
Baseline 1
Operational Environmental
Definition
Operations Safety Assessment
Safety Performance
Requirements
Subgroup 3
Baseline 1
Required Communication
Performance
Subgroup 4
Baseline 2
CPDLC II / LINK 2000+
SC-194
Subgroup 1
CPDLC I/IA
Principles of
Operation
Subgroup 2
Future Applications
Subgroup 3
Human Factors
Subgroup 4
CPDLC IA
ATN G/G IRD
Test Tools
Conformance Test Suite (CTS) /
Common American European
Reference ATN Facility (CAERAF)
Functional Specifications
VDL-2 A/G Comm Service Provider
ARINC 631 - VDL Implementation Spec
ARINC 637 - Transport and Inter-
Networking Protocols
Avionics
ARINC 631 - VDL Implementation
Spec
ARINC 637 - Transport and Inter-
Networking Protocols
ARINC 750 VHF Data Radio
ARINC 758 - CMU
ARINC 638 - Network Management
Ground End Systems
CPDLC I/IA Functional Spec
Petal IIe Trials Spec
Baseline 1
SC-172
VDL-2 MASPS
VDL-2 MOPS
STANDARDS
SPECIFICATIONS

## Slide 26: En Route CPDLC Program Risk Assessment
The following several slides present the En Route Controller Pilot Data Link Communications (CPDLC) Build I program risk assessment results
Includes
  Risk
  Impact
  Mitigation

## Slide 27
Flight Deck Integration
Risk: Flight deck integration may not be agreed upon between American Airlines and Boeing in time to support the PETAL IIE schedule.
Impact: Schedule Slip:
1) American flight deck development
2) American Airlines/Rockwell Collins Communications Management Unit (CMU) development
3) Pilot Human Machine Interface (HMI) study
4) American not able to participate in the PETAL IIE Trials
M
Notes: Risk Item - Flight deck integration and design has not been solidified between American Airlines and Boeing.
Risk Level -Increased from H to H+.
Reason for Change - American Airlines and Boeing TSA was not established by the expected/planned date (i.e., 6/99), increasing probability of CMU development delays.

## Slide 28
Flight Deck Integration (cont.)
Risk Mitigation Strategy:
1. American Airlines is working to establish a Technical Services Agreement (TSA) with Boeing for the 767.
2. FAA Technical Center is working closely with American on prototype flight deck implementations.
3. ARINC and Boeing TSA for CPDLC engineering support is in place.
M

## Slide 29
Funding for RRI Program
Risk: Additional funding required to modify Router Reference Implementation (RRI) product to support ATN over VDL Mode 2 (VDLM2) and VDL handout event.
Impact: Schedule Slip:
1) American Airlines/Rockwell Collins RRI to CMU porting delayed.
2) American not able to participate in the PETAL IIE Trials
H
Notes: Risk Item - Funding required to update RRI program to support ATN over VDL Mode 2.
Risk Level -Increased from H to H+.
Reason for Change - ATNSI announced $2M is required to implement the 8208 change in the RRI. Further, implementing the 8208 change is expected to result in a 5 month RRI development schedule slip (I.e., from 2/00 to 7/00), increasing the likelihood of delays in CMU development and PETAL II trails.

## Slide 30
Funding for RRI Program (cont.)
Risk Mitigation Strategy:
1. FAA/ATNSI/ARINC/Rockwell stabilized Hand-Off Event requirements in AEEC standard.
2. ATNSI/ACI/Rockwell to coordinate RRI schedule revision (with VDLM2 changes) to support existing release date for Rockwell CMU.
3. Rockwell Collins is examining alternative sources for the ISO 8208 code.
4. ATNSI actively seeking additional funding sources.
H

## Slide 31
Router Reference Implementation
Risk: ACI Router Reference Implementation (RRI) software development may not meet original ATNSI contract schedule with full RTCA DO-178b Level C compliance.
Impact: Schedule Slip:
1. FAA human factors demonstration delayed
2. American Airlines/Rockwell Collins RRI to CMU porting delayed.
3. FAA DLAP development delayed.
M

## Slide 32
Router Reference (cont.)
Risk Mitigation Strategy:
1. ACI has developed a schedule recovery plan that is currently on track to deliver on time.
2. FAA has risk mitigation plan using ProATN as backup for RRI for Human Factors Demonstration.
3. FAA Technical Re-Usable Software Team (TRUST) reviewing RRI software for DO-178b compliance.
4. ACI reporting Earned Value Metrics to CPDLC Integration Team monthly meetings.
H

## Slide 33
Certification of Avionics
Risk: Certification of CMU Avionics using the RRI product may delay delivery to American Airlines.
Impact: Schedule Slip:
1. American Airlines/Rockwell Collins CMU installation delayed.
2. American not able to participate in the PETAL IIE Trials
H

## Slide 34
Certification of Avionics (cont.)
Risk Mitigation Strategy:
1. Operational Environment Definition (OED) and Operational Safety Assessment (OSA) activities underway to establish safety requirements.
2. American Airlines and FAA flight standards/certification actively engaged in regular meetings.
3. American Airlines certification plan is under development.
4. FAA Technical Re-Usable Software Team (TRUST) has been established to determine certification policy for RRI porting to CMU’s.
H

## Slide 35
Human Factors Issues
Risk: Data Link Human Factors issues, if not properly addressed, could impact successful CPDLC implementation.
Impact: Operational Implementation not successful.
M

## Slide 36
Human Factors Issues (cont.)
Risk Mitigation Strategy:
1. Data Link Human Factors plan developed and is being followed by all participants.
2. Extensive ground system Human Factors studies conducted over the last 10 years.
3. Controller/Ground System activities on track. Completed initial controller evaluation of Build I services implemented on the Display System Replacement. Detailed planning underway for controller evaluation of Build IA services, training, and procedures.
4. Pilot/Flight deck evaluation underway at the FAA Technical Center. Completed initial pilot review of candidate message alerting and display capabilities. Detailed planning underway for comparative evaluation of configuration alternatives.
5. End-to-end Human Factors Demonstration will provide evidence of successful human factors implementation in December of 2000.
M

## Slide 37
Router Selection
Risk: FAA’s & American Airlines use of ATNSI’s router versus ARINC’s use of AIRTEL’s ATN router poses a potential interoperability problem.
Impact:
Schedule Slip: Rewrite of RRI or AIRTEL software could not be absorbed in current schedule.
Cost overrun: Cost of RRI ground router software rewrite not in FAA CPDLC budget or AIRTEL ground router software rewrite not in ARINC VDL-2 budget.
M

## Slide 38
Router Selection (cont.)
Risk Mitigation Strategy:
1. ARINC to conduct Air/Ground (A/G) interoperability testing with Rockwell and AA; and, A/G & Ground/Ground (G/G) interoperability testing with the FAA.
2. The Conformance Test Suite (CTS) will be used to test interoperability.
3. A letter has been provided to ARINC addressing the FAA’s concern over the use of the AIRTEL router.
4. ARINC responded to FAA letter with a commitment to work together with the FAA and the Airline Industry to ensure the end-to-end system is fielded, fully operable, and supports CPDLC program requirements.
M

## Slide 39
FAA and Industry Integration
Risk: Complex integration requirements for FAA and Industry partners’ activities presents significant risks to achieving CPDLC operational capability.
Impact: Schedule slips due to miscommunication and poor coordination.
M

## Slide 40
Integration (cont.)
Risk Mitigation Strategy:
1. FAA and Industry partners have embraced the development of an integrated schedule that identifies activities, milestones, and interdependencies between all the players.
2. FAA and Industry partners established the CPDLC Integration Team (CIT) that meets on a monthly basis to review progress and track activities against the integrated schedule.
3. FAA, under the AND-1 signature, will make a formal request to Boeing to become a member of the CIT and participate in monthly meetings.
4. FAA and MITRE dedicating considerable full time staff resources to support the integration and coordination of CPDLC Build I.
M

## Slide 41: En Route CPDLC
Back-Up Slides

## Slide 42: CPDLC I Messages
Transfer of Communication (TOC), Initial Contact (IC), Altimeter Setting (AS), and an informational free text menu capability, which will be built by supervisory input and assigned to specified positions.
Notes: <number>
<footer>
<header>
<date/time>

## Slide 43: CPDLC IA Messages
Increase the message set to accommodate assignment of speeds,
headings, altitudes as well as a route clearance function
A capability to handle limited pilot-initiated altitude requests
Added messages are:
Notes: <number>
<footer>
<header>
<date/time>

## Slide 44
Acronyms
A/G Air-to-Ground
ADL Aeronautical Data Link
AF Airway Facilities
ARTCC Air Route Traffic Control Center
ASE Application Service Element
AT Air Traffic
ATC Air Traffic Control
ATN Aeronautical Telecommunication Network
ATNSI Aeronautical Telecommunication Network Systems Inc.
ATSU Air Traffic Services Unit
CDR Critical Design Review
CIT CPDLC Integration Team
CM Context Management
CMA Context Management Application
CMU Communications Management Unit
CPDLC Controller Pilot Data Link Communications
DLAP Data Link Application Processor
DSR Display System Replacement
FAA Federal Aviation Administration
G/G Ground-to-Ground
HF Human Factors
HID Host Interface Device
ICAO International Civil Aviation Organization
IOC Initial Operational Capability
JRC Joint Resource Council
MPS Maintenance Processor System
NADIN II National Airspace Data Interchange Network II
NAS LAN National Airspace System Local Area Network
NEXCOM Next Generation A/G Communications System
NSM Network System Manager
OSA Operational Safety Assessment
OT&E Operational Test & Evaluation
PETAL II Preliminary EUROCONTROL Test of air/ground data Link II
RRI Router Reference Implementation
SARPs Standards And Recommended Practices
TIM Technical Interchange Meeting
VDL-2 VHF Digital Link Mode 2
VDL-3 VHF Digital Link Mode 3
VDR VHF Digital Radio