AERONAUTICAL TELECOMMUNICATION NETWORK PANEL

CCB Standing Document

ATNP Configuration Control Board (CCB) Procedures Document

Edited by CCB Chair

SUMMARY

This document contains detailed procedures to be followed and information necessary to participate in the ATN Panel Configuration Control Board change control process.  As part of this information, this paper defines formats to be used for submission of Validation Report Configuration Items (VRCIs), including Defect Reports, Change Requests and Change Proposals, and participation requirements, roles and responsibilities for VRCI submittors, CCB members, Configuration Manager and WG2 members to be used for the exchange of and decisions regarding these VRCIs.

Version 2.0 of this document includes revised procedures requiring inclusion of changes to the ATN Requirements Database in submitted Change Requests and Change Proposals to be consistent with CNS/ATM-1 SARPs.

REVISION HISTORY

| Section | Date | Issue | Reason for Change |
| --- | --- | --- | --- |
|  | 20 January 1995 | Issue 1.0 | Document Creation |
|  | 06 February 1995 | Issue 1.1 | Separation from Archive Document |
|  | 15 April 1996 | Issue 2.0 | Inclusion of Requirements Database Modification Requirements |

TABLE OF CONTENTS

1. Scope and Purpose of this Paper

2. Definitions

2.1. ICAO ATN Manual 2nd Edition

2.2. ATN Manual Validation Copy (19 November 1993)

2.3. Version n.m ATN SARPs

2.4. Version 0.0 ATN SARPs

- Validation Report Configuration Item (VRCI)

- ATN Requirements Listing (ARL) Index Reference

3. Acronyms

4. Overview of ATN Internet CCB Validation Forms

4.1. Defect Report (DR)

4.2. Change Request (CR)

4.3. Change Proposal (CP)

5. Change Control Process Flow

5.1. Initiation of a Change

5.2. Change Control Decision Making Process

5.3. Detailed Change Proposals

5.4. VRCI Status and Relationship Reports

5.5. ATN Internet CCB Meetings

6. ATN Internet CCB Report Forms

6.1. Defect Report

6.1.1. Defect Report Form

6.1.1.1. “TO” Address

6.1.1.2. “SUBJECT” Field

6.1.1.3. Message Body

6.1.2. Defect Report Form Legend

6.2. Change Request

6.2.1. Change Request Form

6.2.1.1. “TO” Address

6.2.1.2. “SUBJECT” Field

6.2.1.3. Message Body

6.2.2. Change Request Form Legend

6.3. Change Proposal

6.3.1. Change Proposal Form

6.3.1.1. “TO” Address

6.3.1.2. “SUBJECT” Field

6.3.1.3. Message Body

6.3.2. Change Proposal Form Legend

6.4. VRCI Update Proposal

6.4.1. VRCI Update Proposal Message

6.4.1.1. "TO" Address

6.4.1.2. "SUBJECT" Field

6.4.1.3. Message Body

6.4.2. VRCI Update Proposal Message Legend

6.5. CCB Decision

6.5.1. CCB Decision Message

6.5.1.1. "TO" Address

6.5.1.2. "SUBJECT" Field

6.5.1.3. Message Body

6.5.2. CCB Decision Message Legend

7. ATNP CCB Emailing Lists

ATNP Configuration Control Board (CCB) Procedures Document

# 1.	Scope and Purpose of this Paper

This document is the standing document describing the procedures of operation used by the ATNP/WG2 Configuration Control Board (CCB).

This paper contains detailed procedures for the configuration management aspects of the ATN Internet Configuration Control Board (CCB) change control process.  This paper also defines formats to be used for submission of Validation Report Configuration Items (VRCIs), including Defect Reports, Change Requests and Change Proposals, and defines the electronic mail procedures to be used for the exchange of these VRCIs among the active members of the ATN Internet CCB and WG2.

This document is revised and updated based on agreements among members of the ATN Internet CCB and instructions of ATNP WG2.  Version 2.0 of this document reflects assignment of editorial responsibility for the ATN Requirements Database to EUROCONTROL.  Version 2.0 also contains requirements and procedures for authors of Change Requests and Change Proposals to include proposed changes to the ATN Requirements Database to correspond with changes proposed for the CNS/ATM-1 SARPs.

## 1.1.  ATN Requirements Database

Revisions to the purpose and structure of the ATN Requirements Database were considered and approved at ATNP WG2 meetings 6 and 7 in Banff and Brisbane respectively.  The revised structure of the ATN Requirements Database is intended to facilitate tracing of  ATN system requirements to the level necessary to achieve an adequate level of validation coverage of the CNS/ATM-1 SARPs.  To this end, the ATN Requirements Database is organized to identify all ATN Requirements List (ARL) Index references contained in the CNS/ATM-1 SARPs and to provide appropriate table entries for each.

To ensure accurate updating of the ATN Requirements Database, all proposed changes in Change Request and Change Proposal documents must include references to both the appropriate SARPs sections and also to the corresponding ATN Requirements Database ARL Index references.

EUROCONTROL has been tasked with the revision, update and maintenance of the ATN Requirements Database and will function as the Database editor.

# 2.	Definitions

The definitions below are provided for context in this document.  They are derived from WG2-WP/2.  This is not necessarily the primary source for these definitions.

## 2.1.	ICAO ATN Manual 2nd Edition

This term is used to refer to the document that ICAO will publish in the near future based on SICASP/5 Recommendation 3/1.  This document is the result of ICAO applying changes agreed at SICASP/5 (SICASP/5-WP/55) to the draft 1 September 1993 version of the Manual text that was presented to SICASP/5 as SICASP/5-WP/7.  It is understood that ICAO will make additional changes to these in order to make the material suitable for publication as an ICAO Manual.  A draft version of the ICAO ATN Manual (2nd Edition) was presented to ATNP/1 as ATNP/1-WP/4.

## 2.2.	ATN Manual Validation Copy (19 November 1993)

Recognizing that ICAO would require a certain time to finalize the “ICAO ATN Manual (2nd Edition)” as an official ICAO publication, an ad-hoc group of experts from the SICAS Panel delegations created (during the SICASP/5 meeting) the “ATN Manual Validation Copy  (19th November 1993)”.  This  was created by applying the  SICASP/5 agreed changes (SICASP/5-WP/55)  to the draft 1 September 1993 version of the Manual text that was presented to SICASP/5 as SICASP/5-WP/7.  This validation copy has been  the basis of  ATN validation activities that are in progress within various States and Organizations.   ATNP/1 noted a number of differences  between the “Validation Copy” and ATNP/1-WP/4, and was informed that the ICAO Secretariat will resolve any differences between these two documents by applying appropriate modifications to ATNP/1-WP/4 prior to publication of the official second edition of the ATN Manual.

## 2.3.	Version n.m ATN SARPs

Each version of draft SARPs and Guidance Material is explicitly referenced as “n.m”.  In this usage, “n” represents the major revision level associated with agreements reached during a meeting of ATNP Working Group 2, and where “m” represents minor revisions applied between WG2 meetings based on interim agreements by appropriate experts, subject to WG2 approval.

## 2.4.	Version 0.0 ATN SARPs

This version of the draft ATN SARPs and Guidance Material is functionally and technically equivalent to the ATN Manual Validation Copy described above.

## 2.5.	Validation Report Configuration Item (VRCI)

This is the general term used to refer to the group of ATN Internet Configuration Control Board validation forms comprising the Defect Report, the Change Request and the Change Proposal.

## 2.6.  ATN Requirements Listing (ARL) Index Reference

The ARL refers to a unique index listing assigned to each requirement and recommendation in the CNS/ATM-1 Internet SARPs and entered in specific tables in the ATN Requirements Database.  The primary objective of these ARL table entries is to provide an unambiguous reference to SARPs elements so that they can be linked to validation objectives, exercises and results.

# 3.	Acronyms

| ARL | ATN Requirements List |
| --- | --- |
| CCB | Configuration Control Board |
| CM | Configuration Management |
| CP | Change Proposal |
| CR | Change Request |
| DR | Defect Report |
| REC | ATN Requirements Database Recommendation |
| VACM | Validation Archive Configuration Manager |
| VRCI | Validation Report Configuration Item |

# 4.	Overview of ATN Internet CCB Validation Forms

## 4.1.	Defect Report (DR)

Defect Report forms will record and describe any editorial and/or technical defect that has been identified in the text of a Version n.0 draft of the ATN SARPs & Guidance Material document.

The format for a Defect Report is defined in this paper.  Any defects found in the current version of the draft ATN SARPs and Guidance Material are to be reported by submitting a defect report.  Identified defects may be the result of a paper analysis, simulation activities or implementation activities.  A defect report may be submitted by any ATNP Member or Advisor (with his Member’s approval).

## 4.2.	Change Request (CR)

CRs are submitted to change high level requirements which can either be the requirements of the system users as understood by direct interaction (User Requirements) or requirements on the system infrastructure which may not be perceived by direct interaction of the system user, but are necessary for correct operation of the system (Operational Requirements).  These "high-level" requirements (e.g. specific performance requirement change in terms of routing stability, etc.) which is proposed to be added or modified in the text of a Version n.0 draft ATN SARPs & Guidance Material.  Such Change Requests might be issued from external inputs (such as ATNP/WG1 Working Papers) and may result in the creation of new Defect Reports if the new requirement cannot be met with based on other related technical requirements contained in the Version n.m draft ATN  SARPs document.

The format for a Change Request is defined in this paper.  The intent of the CR is to provide a means of  allowing ATNP Members/Advisors to identify and define new requirements or functionalities that are not reflected in the current version of the draft n.0 ATN SARPs and Guidance Material.  A CR may either be directly presented to WG2 or result in a Defect Report which is then presented to WG2.  Change Requests must propose changes to specific sections of the CNS/ATM-1 SARPS and also to the corresponding ARL Index Reference(s) in the ATN Requirements Database.

## 4.3.	Change Proposal (CP)

Change Proposals will typically be created to propose a solution to defects or specification changes identified in Defect Reports and Change Requests.  They should include the proposed modifications, additions, and/or deletions to the draft n.0 ATN SARPs and Guidance Material in a format that will facilitate their direct implementation once approved by the Working Group.

The format for a Change Proposal is defined in this paper.  Change Proposals will be provided in response to a Defect Report or a Change Request that requires resolution, and will be indexed to the appropriate DR(s) and/or CR(s).  In the interest of supporting the timely resolution of proposals, DR or CR originators are encouraged to include draft CP text in the body of the proposed DR or CR, where appropriate. Change Proposals must propose changes to specific sections of the CNS/ATM-1 SARPS and also to the corresponding ARL Index reference(s) in the ATN Requirements Database.

# 5.	Change Control Process Flow

ATNP Working Group 2 has agreed on a process flow which outlines the procedure to be followed to record, process, and trace all Defect Reports (DRs), Change Requests (CRs), and Change Proposals (CPs) which will be generated in the context of the ATN Manual validation work.

## 5.1.	Initiation of a Change

In order to ensure that Defect Reports and Change Requests represent relatively mature proposals, it is recommended that the technical issues contained in defects or changes formally proposed using these forms be first discussed using the “atn-internet-technical” mailing list among interested ATN experts (the use of this facility is described later in this paper).  Once a common understanding of the issue raised in the discussion is reached, a mature DR or CR should be submitted.  These submissions must be made using the appropriate electronic forms, and are sent to the “ATN Validation Archive” Configuration Manager who is in charge of assigning an identifying number to the report, storing the form in the proper Archive Directory, and posting an information message reporting the submission of the new report or proposal  in the “atn-internet-vrci” mailing list in the case of DRs and CPs, and in the "atn-internet-technical" mailing list in the case of CRs.  This posting will mark the beginning of the 2 weeks period of formal consideration of the proposed defect or change by the ATN Internet CCB.

## 5.2.	Change Control Decision Making Process

The CCB and Working Group 2 (respectively) will decide whether the submitted DR or CR, documents an appropriately mature and necessary change to the Version n.0 draft SARPs and Guidance Material document.  If the defect or requirements change is deemed to be sufficiently abstract or complex, CCB members may opt to make this decision pending review of corresponding submitted CP(s) or validation information based on implementation or simulation.  Subsequent to the acceptance of the validity of the proposed defect or requirements change, each reviewed DR and CR will then be updated accordingly (i.e. new Status field, and completion of the “CCB Recommended Action” field).

The CCB Decision making process will be performed in three steps:

1.	After the receipt of a SUBMITTED VRCI, ALL CCB members must propose a new status for this VRCI, with supporting arguments if appropriate, via a so-called 'VRCI Update Proposal' message sent to "atn-internet-vrci" within the 2 weeks VRCI reviewing period.  The format of the 'VRCI Update Proposal' message is presented in section 6.4.

2.	Not later than one week after the end of the 2 weeks VRCI reviewing period, the CCB Chairman will compile the 'VRCI Update Proposal' messages and elaborate a 'CCB Decision' message reflecting the majority opinion.  This message will be sent on the 'atn-internet-technical' mailing list in order to notify the ATN community about the proposed CCB decision.  In addition, the 'CCB Decision' message will also be sent to the atn-internet-cm address for updating and distributing the archived VRCI.

3.	Upon receipt of a 'CCB Decision' message from the CCB Chairman, the Configuration Manager will update the archived VRCI (i.e. 'Status' and 'CCB Recommended Action' fields), and send the updated version on the 'atn-internet-vrci' list.

With respect to CRs lack of response by WG2 members will indicate “don’t care” as opposed to the “responsibility to respond” requirement on CCB members for DRs and CPs.

In cases where DRs are outstanding without CPs, these cases will be reviewed regularly to see if the CCB or WG2 can initiate action to promote closure of these defects.  Agreed CPs will be submitted to the ATNP Secretary for change to the ICAO ATN Manual.  If a change proposal without a defect report or change request is submitted it will be rejected by CM with the author notified.  Files attached to or referenced by VRCIs should be sent with readme.txt to the validation archive for direct access.  Procedures and access information for this archive will be available in the Configuration Management Plan CCB standing document.

The diagram below delineates the submissions, responses and decision points in the process.  The CCB members make the CCB decision described in the diagram, which is collated by the CCB Chair.  CCB members must be subscribed to the two mailing lists described in the figure (i.e. atn-internet-technical, atn-internet-vrci), but anyone else may be subscribed to stay informed with the status of the draft SARPs and ability to provide comments at any stage of the process.

Figure 1: CCB Remote Process Diagram

## 5.3.	Detailed Change Proposals

Either directly after the distribution of a DR or CR by the VACM, or following the acceptance of the DR or CR, the DR/CR author and/or other interested parties will develop one or more Change Proposals to describe required elements of the solution and/or change text.

The elaboration of proposed detailed changes will consist of:

a)	applying the CCB or WG recommended action (analysis, simulation, and/or implementation) if any in order to elaborate and validate a solution to the reported defect or change request.

b)	submitting a Change Proposal (CP) for CCB review once the solution to fix the defect or satisfy the change request has been validated.

Change Proposal forms are used to record and describe all editorial and/or technical modifications to the text of the Version n.0 draft ATN SARPs, the Guidance Material documents and also to the ATN Requirements Database.  Such forms trace the origin of the proposed change (DR or CR), describe the change itself, and explain how the proposed change has been validated.  CPs should also be discussed in the “atn-internet-technical” mailing list before being issued through the same process as DRs and CRs (i.e. send the CP to the VACM who will assign the CP number, store it in the Archive and post an information message).

All submitted CPs will be reviewed by the ATN Internet CCB, which may assign a status of  Accepted, Rejected, Pending, Withdrawn, or Implemented.  If several CPs are proposed as a solution to one or several DR(s) or CR(s), the ATN Internet CCB must reach consensus on a single solution and associated Change Proposal.  Accepted CPs will then be proposed to the WG2 for formal agreement and will then be considered as Agreed Changes, with WG2 agreed Change Proposals also being reported to the ATN Panel Secretary for application to the current baseline version of the ATN Manual.

## 5.4.	VRCI Status and Relationship Reports

In order to advise CCB Members and any interested party of the linkage among VRCIs managed by the ATNP CCB VACM, a report of VRCI status and relationships will be created periodically by the VACM, and will be distributed to the 'atn-internet-technical' mailing list previously discussed in this paper.  This report will also be archived on the ATNP CCB CM system for ftp retrieval by interested parties.  The period at which these reports will be issued may vary depending on CCB activity, but will not be shorter than 1 week and not longer than 1 month.

## 5.5.	ATN Internet CCB Meetings

In general, ATN Internet CCB proceedings will be conducted using the email tools documented later in this paper.  However, when considered necessary by the CCB Chair, a CCB meeting may be convened for review of outstanding DRs, CRs, and CPs, in order to formulate recommendations to the WG.  CCB meetings may be convened between WG2 meetings, or consecutively with WG2 meetings, as is deemed necessary.  In this case, DRs, CRs, and CPs to be reviewed by the ATN Internet CCB should be made available to its members 2 weeks before the associated meeting.

6.	ATN Internet CCB Report Forms

Figure 2: Change Control Procedure for ATN SARPs and Guidance Material

Forms to be used for the ATN Internet CCB Configuration Management process are contained in the following sections.

## 6.1.	Defect Report

### 6.1.1.	Defect Report Form

An ATN Internet CCB Defect Report form shall have the format described in the following sub-sections.

#### 6.1.1.1.	“TO” Address

This should be sent to the atn-internet-cm list, the current internet address for this will be found in the Configuration Management Plan document.

#### 6.1.1.2.	“SUBJECT” Field

DR <dd/mm/yy> <title>

Activation of the VACM automated process for VRCI submission will only be possible if the following conventions are carefully respected:

-	The presence of the three items is required (i.e. "DR", the date, and the title)

-	A single <space> character must be inserted between "DR" and the date, and between the date and the <title> text,

-	"/" characters are required as separators in the date as well as exactly 2 digits per field,

-	The length of the <title> field should not exceed 40 characters.  It will be used by the VACM automated process to fill the actual 'Title' field in the DR form.

#### 6.1.1.3.	Message Body

Title:

Defect Report Reference:

Status: <SUBMITTED/PENDING/REJECTED/ACCEPTED/WITHDRAWN/RESOLVED>

Defect Report Revision Date: <dd/mm/yy>

Defect Report Format Revision Date: 20 January 1995

Defect Report Submission Date:<dd/mm/yy>

Submitting State/Organization: <Panel Member/Observer>

Submitting Author Name: <Last Name, First Initial>

Submitting Author E-mail Address: <Internet EMAIL Address>

Submitting Author Supplemental Contact Information:

ATN SARPs & Guidance Material Draft Version:

SARPs/GM Document Reference: <requirement number, section, page number, figure or table number, as appropriate>

Category: <EDITORIAL/MINOR/MAJOR>

Summary of Defect:

Discussion:

Related Requirements:

CCB Decision Date:

CCB Recommended Action:

### 6.1.2.	Defect Report Form Legend

| Field | Format | Comments |
| --- | --- | --- |
| Title | TEXT | Short description of the subject of the Defect. This field is assigned by the Configuration Manager from the <title> field contained in the 'Subject' line of the submission message. It should not be filled by the author of the DR. |
| Defect Report Reference: | IDENTIFIER | Unique identifier assigned by the Configuration Manager |
| Status: | SUBMITTED/PENDING/REJECTED/ACCEPTED/WITHDRAWN/RESOLVED | Status assigned by the Configuration Manager: SUBMITTED, i.e. the report has been submitted but has not yet been reviewed yet by the Change Control Board; PENDING, i.e. the report has been reviewed by the Change Control Board, but for certain reasons (i.e. typically, the need to provide additional information), has not yet been formally accepted or rejected; REJECTED, i.e. the CCB did not recognize the content of the report as being a defect or required change; ACCEPTED, i.e. the CCB recognized that the report documents an actual defect or required change (see then recommended action); WITHDRAWN, i.e. the problem needed further investigation and when clarifications are possible, a new defect report will be issued. RESOLVED, i.e. the problem has been solved by the implementation of an accepted Change Proposal(s). |
| Defect Report Revision Date: | DATE (dd/mm/yy) | Latest revision date at which the report was updated; this field is assigned by the Configuration Manager upon receipt of a 'CCB Decision' message |
| Defect Report Format Revision Date: | 20 January 1995 | Version identification for the report format, assigned by the Configuration Manager |
| Defect Report Submission Date: | DATE (dd/mm/yy) | Date at which the report is received by the configuration manager; this field is assigned by the VACM upon receipt of a correct DR submission message. |
| Submitting State/Organization: | TEXT | ICAO ATNP Member/Observer |
| Submitting Author Name: | TEXT | <Last Name, First Initial> |
| Submitting Author E-mail Address: | TEXT | Internet EMAIL Address |
| Submitting Author Supplemental Contact Information: | TEXT | Postal Address, Telephone, FAX |
| ATN SARPs & Guidance Material Draft Version: | TEXT | Version n.0 |
| SARPs/GM Document Reference: | TEXT | Related or affected requirement number, section, page number, figure or table number, as appropriate. |
| Category | EDITORIAL/ MINOR/MAJOR | EDITORIAL, i.e. the reported defect is a pure editorial problem, and raises no technical issue; MINOR, i.e. the reported defect raises a minor technical problem; MAJOR, i.e. the reported defect raises a significant technical problem which may require thorough study before being resolved. |
| Summary of Defect: | TEXT | Brief presentation of the problem. |
| Discussion: | TEXT | Detailed description of the problem and impacts on other requirements. |
| Related Requirements: | TEXT | List of database entries (Requirements, recommendation, options, etc.) which are involved or affected. |
| CCB Decision Date | DATE (dd/mm/yy) | Date at which action is formally taken by the CCB to close this report. |
| CCB Recommended Action: | TEXT | Action recommended by the CCB in order to find a solution or validate solutions for this problem. This field is filled by the VACM by appending relevant information contained in the successive 'CCB Decision' messages received about this DR. |

## 6.2.	Change Request

### 6.2.1.	Change Request Form

An ATN Internet CCB Change Request form shall have the format described in the following sub-sections.

#### 6.2.1.1.	“TO” Address

This should be sent to the atn-internet-cm list, the current internet address for this will be found in the Configuration Management Plan document.

#### 6.2.1.2.	“SUBJECT” Field

CR <dd/mm/yy> <title>

Note:  see section 6.1.1.2 (i.e. DR "SUBJECT" field) for advice on how to use this field..

#### 6.2.1.3.	Message Body

Title:

Change Request Reference:

Status: <SUBMITTED/PENDING/REJECTED/ACCEPTED/WITHDRAWN/IMPLEMENTED>

Change Request Revision Date: <dd/mm/yy>

Change Request Format Revision Date: 20 January 1995

Change Request Submission Date: <dd/mm/yy>

Submitting State/Organization: <Panel Member/Observer>

Submitting Author Name: <Last Name, First Initial>

Submitting Author E-mail Address: <Internet EMAIL Address>

Submitting Author Supplemental Contact Information:

ATN SARPs & Guidance Material Draft Version:

SARPs/GM Document Reference: <requirement number, section, page number, figure or table number, as appropriate>

ATN Requirements Database ARL Index/Item Reference:

Category: <EDITORIAL/MINOR/MAJOR>

Summary of Change:

Discussion:

Related Requirements:

CCB Decision Date:

CCB Recommended Action:

### 6.2.2.	Change Request Form Legend

| Field | Format | Comments |
| --- | --- | --- |
| Title | TEXT | Short description of the subject of the Change. This field is assigned by the Configuration Manager from the <title> field contained in the 'Subject' line of the submission message. It should not be filled by the author of the CR. |
| Change Request Reference: | IDENTIFIER | Unique identifier assigned by the Configuration Manager |
| Status: | SUBMITTED/PENDING/REJECTED/ACCEPTED/WITHDRAWN/IMPLEMENTED | Status assigned by the Configuration Manager: SUBMITTED, i.e. the report has been submitted but has not yet been reviewed yet by the Change Control Board; PENDING, i.e. the report has been reviewed by the Change Control Board, but for certain reasons (i.e. typically, the need to provide additional information), has not yet been formally accepted or rejected; REJECTED, i.e. the CCB did not recognize the content of the report as being a defect or required change; ACCEPTED, i.e. the CCB recognized that the report documents an actual defect or required change (see then recommended action); WITHDRAWN, i.e. the problem needed further investigation and when clarifications are possible, a new Change Request will be issued; IMPLEMENTED, i.e. the change has been accepted and incorporated in the Draft SARPs & Guidance Material document. |
| Change Request Revision Date: | DATE (dd/mm/yy) | Latest revision date at which the report was updated; this field is assigned by the Configuration Manager upon receipt of a 'CCB Decision' message. |
| Change Request Format Revision Date: | 20 January 1995 | Version identification for the report format, assigned by the Configuration Manager |
| Change Request Submission Date: | DATE (dd/mm/yy) | Date at which the report is received by the configuration manager; this field is assigned by the CM upon receipt of a correct CR submission message. |
| Submitting State/Organization: | TEXT | ICAO ATNP Member/Observer |
| Submitting Author Name: | TEXT | <Last Name, First Initial> |
| Submitting Author E-mail Address: | TEXT | Internet EMAIL Address |
| Submitting Author Supplemental Contact Information: | TEXT | Postal Address, Telephone, FAX |
| ATN SARPs & Guidance Material Draft Version: | TEXT | Version n.0 |
| SARPs/GM Document Reference: | TEXT | Related or affected requirement number, section, page number, figure or table number, as appropriate. |
| ATN Requirements Database ARL Index/Item Reference: | TEXT | Related or affected ARL Index or Item corresponding to SARPs Reference. |
| Category | EDITORIAL/ MINOR/MAJOR | EDITORIAL, i.e. the requested change is a pure editorial modification, and raises no technical issue; MINOR, i.e. the requested change raises a minor technical issue; MAJOR, i.e. the requested change raises a significant technical issue which may require thorough study before being decided. |
| Summary of Change: | TEXT | Brief presentation of the change. |
| Discussion: | TEXT | Detailed description of the change and impacts on other requirements. |
| Related Requirements: | TEXT | List of database entries (Requirements, recommendation, options, etc.) which are involved or affected. |
| CCB Decision Date | DATE (dd/mm/yy) | Date at which action is formally taken by the CCB to close this report. |
| CCB Recommended Action: | TEXT | Action recommended by the CCB in order to find a solution or validate solutions for this problem. This field is filled by the VACM by appending relevant information contained in the successive 'CCB Decision' messages received about this CR. |

## 6.3.	Change Proposal

### 6.3.1.	Change Proposal Form

An ATN Internet CCB Change Proposal form shall have the format described in the following sub-sections.

#### 6.3.1.1.	“TO” Address

This should be sent to the atn-internet-cm list, the current internet address for this will be found in the Configuration Management Plan document.

#### 6.3.1.2.	“SUBJECT” Field

CP <dd/mm/yy> <title>

Note:  see section 6.1.1.2 (i.e. DR "SUBJECT" field) for advice on how to use this field..

#### 6.3.1.3.	Message Body

Title:

Change Proposal Reference:

Defect Report or Change Request Reference:

Status: <SUBMITTED/PENDING/REJECTED/ACCEPTED/WITHDRAWN/IMPLEMENTED>

Change Proposal Revision Date: <dd/mm/yy>

Change Proposal Format Revision Date: 20 January 1995

Change Proposal Submission Date: <dd/mm/yy>

Submitting State/Organization: <Panel Member/Observer>

Submitting Author Name: <Last Name, First Initial>

Submitting Author E-mail Address: <Internet EMAIL Address>

Submitting Author Supplemental Contact Information:

ATN SARPs & Guidance Material Draft Version:

SARPs/GM Document Reference: <requirement number, section, page number, figure or table number, as appropriate>

ATN Requirements Database ARL Index/Item Number:

Summary of Proposal:

Discussion:

Impact on Requirements:

CCB Decision Date:

CCB Recommended Action:

### 6.3.2.	Change Proposal Form Legend

| Field | Format | Comments |
| --- | --- | --- |
| Title | TEXT | Short description of the subject of the Change Proposal. This field is assigned by the Configuration Manager from the <title> field contained in the 'Subject' line of the submission message. Note: in case of one-to-one mapping between a CP and a DR, or a CR, the 'Title' field of these two VRCIs should be identical. |
| Change Proposal Reference: | IDENTIFIER | Unique identifier assigned by the Configuration Manager |
| Defect Report or Change Request Reference(s): | IDENTIFIER | Unique identifier(s) assigned by the author of the CP. This is the list of submitted Defect Reports or Change Requests which are proposed to be resolved by this CP. Note: this field is required for the submission of the Change Proposal. |
| Status: | SUBMITTED/PENDING/REJECTED/ACCEPTED/WITHDRAWN/IMPLEMENTED | Status assigned by the Configuration Manager: SUBMITTED, i.e. the report has been submitted but has not yet been reviewed yet by the Change Control Board; PENDING, i.e. the report has been reviewed by the Change Control Board, but for certain reasons (i.e. typically, the need to provide additional information), has not yet been formally accepted or rejected; REJECTED, i.e. the CCB did not recognize the content of the report as being an appropriate solution to the related defect or required change; ACCEPTED, i.e. the CCB recognized that the report documents the appropriate solution to be implemented to close the related DR or CR; WITHDRAWN, i.e. the proposal needed further investigation and when clarifications are possible, a new Change Proposal will be issued; IMPLEMENTED, i.e. the change has been accepted and incorporated in the Draft SARPs & Guidance Material document. |
| Change Proposal Revision Date: | DATE (dd/mm/yy) | Latest revision date at which the report has been updated; this field is assigned by the Configuration Manager upon receipt of a 'CCB Decision' message. |
| Change Proposal Format Revision Date: | 20 January 1995 | Version identification for the report format, assigned by the Configuration Manager |
| Change Proposal Submission Date: | DATE (dd/mm/yy) | Date at which the report is received by the configuration manager; this field is assigned by the CM upon receipt of a correct CP submission message. |
| Submitting State/Organization: | TEXT | ICAO ATNP Member/Observer |
| Submitting Author Name: | TEXT | <Last Name, First Initial> |
| Submitting Author E-mail Address: | TEXT | Internet EMAIL Address |
| Submitting Author Supplemental Contact Information: | TEXT | Postal Address, Telephone, FAX |
| ATN SARPs & Guidance Material Draft Version: | TEXT | Version n.0 |
| SARPs/GM Document Reference: | TEXT | Related or affected requirement number, section, page number, figure or table number, as appropriate. |
| ATN Requirements Database ARL Index/Item Reference: | TEXT | Related or affected ARL Index or Item corresponding to SARPs Reference. |
| Summary of Proposal: | TEXT | Brief presentation of the solution. |
| Discussion: | TEXT | Detailed description of the solution and impacts on other requirements. |
| Impact on Requirements: | TEXT | List of database entries (Requirements, recommendation, options, etc.) which are involved or affected. |
| CCB Decision Date | DATE (dd/mm/yy) | Date at which action is formally taken by the CCB to close this report. |
| CCB Recommended Action: | TEXT | Action recommended by the CCB in order to find a solution or validate solutions for this problem. This field is filled by the VACM by appending relevant information contained in the successive 'CCB Decision' messages received about this CP. |

## 6.4.	VRCI Update Proposal

### 6.4.1.	VRCI Update Proposal Message

A DR or CP 'Update Proposal Message' shall be sent by ALL CCB members to the 'atn-internet-vrci' list, not later than 2 weeks after the submission of the related DR or CP.

A CR 'Update Proposal Message' can be sent by all WG2 members to the 'atn-internet-technical' list, not later than 2 weeks after the submission of the related CR.  CCB members are required to respond to CRs in that period.

Note: silence from WG2 members within this 2 weeks period will indicate "don't care" until next WG2 meeting when the issue may be raised.

#### 6.4.1.1.	"TO" Address

This should be sent to the atn-internet-vrci list, the current internet address for this will be found in the Configuration Management Plan document.

#### 6.4.1.2.	"SUBJECT" Field

PROPOSED UPDATE <VRCI Reference>

Note: <VRCI Reference> in the format yymmnnnn.DR, yymmnnnn.CR, or yymmnnnn.CP

#### 6.4.1.3.	Message Body

WG2/CCB Member Name: <Last Name>

VRCI Reference: <yymmnnnn.VRCI>

New Proposed Status:	<PENDING/REJECTED/ACCEPTED/WITHDRAWN/
				RESOLVED/IMPLEMENTED>

Comments:

### 6.4.2.	VRCI Update Proposal Message Legend

| Field | Format | Comments |
| --- | --- | --- |
| WG2/CCB Member Name | TEXT | <Last Name> |
| VRCI Reference: | IDENTIFIER | Unique identifier of the VRCI for which a new status is proposed. |
| New Proposed Status: | PENDING/REJECTED/ACCEPTED/WITHDRAWN/RESOLVED/IMPLEMENTED | Status proposed for the discussed VRCI. |
| Comments: | TEXT | Short text explaining the reason why the author proposes such a new status for the discussed VRCI. |

## 6.5.	CCB Decision

A CCB Decision Message shall be sent by the CCB Chairman, not later than 1 week after the end of the two weeks VRCI reviewing period.

### 6.5.1.	CCB Decision Message

#### 6.5.1.1.	"TO" Address

This should be sent to the atn-internet-technical list, the current internet address for this will be found in the Configuration Management Plan document.

#### 6.5.1.2.	"SUBJECT" Field

CCB DECISION ON <VRCI Reference>

Note: <VRCI Reference> shall be identical to the filename of the archived VRCI

#### 6.5.1.3.	Message Body

VRCI Reference: <yymmnnnn.VRCI>

Former Status: <SUBMITTED/PENDING/ACCEPTED/WITHDRAWN>

New Status: <PENDING/REJECTED/ACCEPTED/WITHDRAWN/
		RESOLVED/IMPLEMENTED>

Decision date: <dd/mm/yy>

Decision Summary:

CCB Recommended Action:

### 6.5.2.	CCB Decision Message Legend

| Field | Format | Comments |
| --- | --- | --- |
| VRCI Reference: | IDENTIFIER | Unique identifier of the VRCI which has to be updated. |
| Former Status: | SUBMITTED/PENDING/ACCEPTED/WITHDRAWN | Status of the VRCI before the CCB Decision. |
| New Status: | PENDING/REJECTED/ACCEPTED/WITHDRAWN/RESOLVED/IMPLEMENTED | New Status of the VRCI after the CCB Decision. |
| Decision Date: | DATE (dd/mm/yy) | Date at which the VRCI has been updated; this field is used by the Configuration Manager to assign the 'Revision date' field of a VRCI. |
| Decision Summary: | TEXT | Summary of the 'VRCI Update Proposal' messages received prior to the decision on the VRCI new status. |
| CCB Recommended Action: | TEXT | Action recommended by the CCB in order to find a solution or validate solutions for this problem. This field is appended by the VACM to the 'CCB Recommended Action' field of the VRCI. |

# 7.	ATNP CCB Emailing Lists

All current WG2 ATNP Emailing Lists have been established at CENA/Toulouse (France), and are available for use by ATN validation staff having access to the Internet.  These lists are currently composed of three ATN-Internet electronic mail distribution lists.  These lists have been established to support technical interchange and validation activities regarding the ATN Internet.  The abstract names for these lists are:

atn-internet-general

atn-internet-technical

atn-internet-vrci

If email is sent to any of the list addresses, that email will be forwarded to all subscribers to the list to which the email is addressed.  The actual internet addresses corresponding to these lists can be found in the ATNP Configuration Management Plan document which is a companion CCB standing document to this one.  In general, certain conventions for use of the two ATN Internet mailing lists apply.

The atn-internet-general list should be used, for example, for the exchange of:

1.	information of an administrative nature,

2.	information concerning the ATN validation process and associated decision-making,

3.	announcements concerning ATN implementation and demonstration activities, standards activities, related meetings, etc.

The atn-internet-technical list should be used, for example, for:

1.	detailed technical exchanges among ATN implementors and validators,

2.	detailed discussion of proposed solutions to problems identified during the validation process.

3.	dissemination of CRs and related 'CR Update Proposal' messages,

4.	CCB resolutions about submitted VRCIs (i.e. so-called 'CCB Decision' messages)

5.	dissemination of periodic VRCIs status and relationship reports.

The atn-internet-vrci list is provided for:

1.	dissemination of DRs and CPs,

2.	dissemination of 'DR/CP Update Proposal' messages,

3.	any discussion relevant to CCB work.

To subscribe to these lists, reference the CMP document.

Whilst it is preferred that VRCIs are submitted against a Version n.0 of the draft ATN SARPs & Guidance Material document, it is recognized that in the cases where more than one Version n.m of the draft ATN SARPs & Guidance Material document is issued between Working Group 2 meetings, it may be appropriate to issue VRCIs against the most recent Version n.m.