|  | ATNP/WG3/IP/16-02 11 May 1999 |
| --- | --- |

- AERONAUTICAL TELECOMMUNICATION NETWORK PANEL

- WORKING GROUP 2&3

- Naples, May 1999

- Status of the European Link 2000+ Programme

- (Information Paper)

- Prepared by  Eike Meyenberg

- Presented by: Danny Van Roosbroek, Martin Adnams

- SUMMARY

This information paper provides a high level overview of the status of the  Link2000+ Programme for the implementation of ATN based Data Link Services in Europe.

# Introduction

At the previous ATNP meeting in January 1999, an information paper described the establishment of the LINK2000+ programme (further called LINK) to coordinate the implementation of Data Link Services in Europe.

The Eurocontrol Agency established a drafting group to define the LINK programme containing the necessary elements for the stakeholders concerned to commit to the programme in well defined and affordable steps. The programme definition phase has started.

# “Link” Objectives

The objective of the LINK Programme is the implementation of operational air-ground data link services for en-route ATC in the near and medium term (indication 2002 - 2007).

It is a fundamental assumption, that this objective can only be realised by using a communications infrastructure that is shared for both ATC and AOC purposes. The Programme will address the implementation of ATS data link via the ATN as an evolutionary next step, taking advantage of the existence of AOC/ACARS data link services and the synergy between the ATC and AOC data link services.

The objective of the Implementation Planning Phase is to obtain commitment from all stakeholders to proceed with the actual operational implementation. This decision will be based on the acceptance of the conclusions contained in the LINK Master Plan and the LINK Business Case.

It is intended to seek approval for these documents at the Provisional Council in April 2000.

In addition, it is planned to seek endorsement from other senior management bodies, representing the other major stakeholders.

# Scope

The ‘baseline’ scope of the LINK Programme consists of :

- Functionality: implementation of controller pilot data link communications in the en-route environment;

- Geographical: small number of “core area” Area Control Centres (ACC’s) (these ACC’s manage airspace where data link is expected to provide the highest airspace capacity benefits and have flights data processing systems that are technically capable of supporting air ground data link in the time scales of LINK).

- Time scales: 2002-2007

- Aircraft population: Based on discretionary carriage of air-ground data-link communication equipment by the airlines.

# Consultation with Eurocontrol EATMP Teams

The proposal to create the LINK2000+ programme had been presented to the Eurocontrol EATMP (European Air Traffic Management Programme) COMT/14 and ODT/14 meetings, with a request for their support.

The COMT /14 meeting:

- Supported the creation of a programme to perform the implementation planning task;

- Requested that the programme be ‘user driven’, with a strong involvement from the airlines;

- Advised that the upgrade of ATM Data Processing systems was a critical issue;

- Requested that there be close co-ordination with the ATNI Task Force.

The ODT/14 meeting;

- Supported the creation of a programme to perform the implementation planning task;

- Advised that the upgrade of ATM Data Processing systems was a critical issue.

# Main Deliverables and Milestones

The main deliverables/milestones for the Implementation Planning Phase are:

- Eurocontrol EATMP Directors approve Implementation Planning Phase – end May, 1999

- Business Case available – end November, 1999

- Master Plan available –end December, 1999

- Master Plan and Business Case presented to ACG – end February, 2000

- Master Plan and Business Case approved by Provisional Council – end April, 2000

# Business Case

A Business Case Workshop for European Data link Implementation was held on 20-21 April 1999.

The purpose of the workshop was to kick-off preparation for the Business Case development of European Data Link Implementation in the near and mid-term (2002-2007).

It was agreed to include this group in the C/AFT initiative under the name CAFT/Euro Datalink Focused Group.

The CAFT/Euro Datalink Focused Group workshop agreed to develop a Business Case that includes a strategic analysis and a probabilistic Cost Benefit Analysis using the C/AFT model.  To achieve this the group would have to define the European business environment, adapt the C/AFT influence model, to resolve business case issues/assumptions and thereby set actions to collect data, and to discuss the Strategic approach.  The timeframe for completion of these objectives and the delivery of a Business Case for operational mobile data link services for ATC and AOC, and the supporting infrastructure is end 1999 as this will co-inside with the objective of the LINK Drafting group to produce a LINK Programme document which will provide all the arguments for commitment to the programme from stakeholders.  In April 2000 the Provisional Council is to review/approve the Implementation Plan and supporting Business Case.

The meeting schedule for EuroC/AFT is:

- Kick-off (20-21 April)

- Mid-term review workshop (1-2 or 2-3 Sep)

- Final review workshop (end 99)

# Recommendations

The Working Group is invited to note the information in this paper.