ATNP SGA3-WP/2-8

ATNP WGA02-WP-25

AERONAUTICAL TELECOMMUNICATIONS NETWORK PANEL (ATNP)

Honolulu, Hawaii- 27-9 March 2001

Proposed Draft

Of

ASIA PACIFIC Region

ATN Ground Transition Plan

(Presented by Rapporteur of APANPIRG/ATNTTF Working Group B)

Summary

This paper was developed by the APANPIRG ATN TransitionTask Force Ad Hoc Working Group B to lay out the Asia/Pacific Regional ATN Ground Transition Plan.  This paper will be presented to the Third APANPIRG ATN Task Force to be held in Singapore March 26-30 2001.  The purpose of presenting this paper to the ATN Panel Sub Groups is to ensure the planning is in line with the SARPs and to seek constructive comments from other regions to ensure future seamless global ATN service. Subsequently, this regional ATN Ground Transition Plan will be implemented after the review and approval of the APANPIRG.

International Civil Aviation Organization

ATN Implementation Planning Group of APANPIRG/ATNTTF

Proposed Draft

Of The

ASIA PACIFIC Region

ATN Ground Transition Plan

(Prepared by APANPIRG/ATNTTF Working Group B)

(Presented by Rapporteur of APANPIRG/ATNTTF Working Group B)

Summary

This document is presented as a final draft of the ATN Ground Transition Plan for the Asia Pacific Region.

Table of Contents

Executive Summary	2

1.	Introduction	3

1.1	Objectives	3

1.2	Scope	3

1.3	References	3

2.	Existing Ground Infrastructure	3

3.	ATN End System Applications	4

4.	ATN Traffic	5

4.1	Ground-Ground traffic	5

4.2	Air-Ground Traffic	6

5.	ATN Routing Architecture	7

6.	ATN Backbone Trunks	8

7.	Interconnection of ATN Routers	11

8.	Transition Activities	12

8.1	Stage 1	12

8.2	Stage 2	13

8.3	Stage 3	13

9.	Conclusions	13

10.	Recommendations	13

A.	ATN Interconnection Circuits	A-1

B.	Asia Pacific International AFTN	B-1

Executive Summary

This document provides technical guidance on the transition from the ground infrastructure support of the Aeronautical Fixed Telecommunication Network (AFTN) services to the Aeronautical Telecommunication Network (ATN) for the Asia Pacific Region.

Background

The ATN Transition Task Force was assigned a number of tasks to prepare the region for the introduction of the ATN. Task 2 of the task list was to develop an ATN Ground Transition Plan to provide a seamless transition from the AFTN to the ATN. The plan is to also take into consideration the air to ground aspects within the region.

At the second meeting of the Asia Pacific ATN Transition Task Force (ATNTTF) it was decided to establish a second working group called Working Group B who would be responsible for the development of the transition plan.

Overview

This document presents recommendations for the transition activities for the Asia Pacific Region.

# Introduction

This document presents a plan on the ATN ground transition activities applicable to the Asia Pacific region. The document provides information on the ground infrastructure required to support the ATN and to take into consideration the ATN air-to-ground requirements of the region.

## Objectives

The objective of this document is to provide guidance and information on the transition activities that will need to occur for the Asia Pacific region to migrate from the AFTN to the ATN.

The document also takes into account the air-ground aspects as promoted by the ATN Routing Architecture Plan (Reference 2).

## Scope

The scope of the document includes:

- A brief description of the existing ground infrastructure based on AFTN;

- The types of ATN applications that will be used over the ground infrastructure;

- The types of trunks that will need to be upgraded to cater for ATN traffic; and

- A proposed implementation schedule on how the ATN should be transitioned within the region.

## References

Reference 1		Manual of Technical Provisions for the ATN  (Doc 9705-AN/956) Second Edition 1999.

Reference 2	ATN Routing Architecture Plan for the Asia Pacific Region

Reference 3	ICAO Location Indicators – Document 7910/94

Reference 4	ICAO Asia Pacific CNS Facilities And Services Implementation Document

# Existing Ground Infrastructure

Figure B-3 shows the current AFTN topology as of August 2000. The existing AFTN is mainly made up of low speed circuit links operating at 600 bps to 9600 bps using X.25 or asynchronous protocols. There are also a number of low speed circuits operating at 50 baud using telegraph technology. Currently there are over 90 International AFTN circuits that operate within the Region and between neighbouring regions. Further details for each AFTN circuit within the Asia Pacific Region is documented in the ICAO Asia Pacific CNS Facilities And Services Implementation Document (FASID) (Reference 4).

When reviewing the current AFTN topology, the majority of AFTN circuit links will not be suitable to be used for the ATN without some form of upgrade. These upgrades will need to be in the form of high-speed links (bandwidth capacity) and the use of modern protocols such as X.25 that is compatible with the ATN lower layers.

It can also be assumed that due to different planning activities by States, that not all States within the region will be migrating to the ATN at the same time. Therefore there will be a need to maintain existing AFTN circuit links to operate in parallel with any new implementation of high-speed links to meet ATN requirements.

It may also be possible for some States that operate private subnetworks using protocols such as X.25 that they could be in a position to carry transit ATN traffic between States that have implemented ATN without being forced to implement ATN in their own country straight away. This would allow the progression of the ATN to continue within the Region without being restricted or having to operate expensive links as a temporary measure while waiting for other States to start their implementation programs.

# ATN End System Applications

There are currently six end system applications identified in the Manual of Technical Provisions for the ATN (Reference 1). Table 3-1 lists these applications and provides a brief summary of their functions.

Table 3-1 ATN Applications

| Application | Function |
| --- | --- |
| Context Management (CM) | An ATN application that provides a logon service allowing initial aircraft introduction into the ATN and a directory of all other data link applications on the aircraft. |
| Automatic Dependent Surveillance (ADS) | An ATN application that provides data from the aircraft to the ATS unit(s) for surveillance purposes. |
| Controller Pilot Data Link Communication (CPDLC) | An ATN application that provides a means of ATC data communication between controlling, receiving or downstream ATS units and the aircraft, using air-ground and ground-ground subnetworks. |
| Flight Information Service (FIS) | An ATN application that provides to aircraft information and advice useful for the safe and efficient conduct of flight. |
| ATS Message Handling System (AMHS) | The set of computing and communication resources implemented by ATS organisations to provide the ATS message service. |
| ATS Inter-facility Data Communication (AIDC) | An ATN application dedicated to exchanges between ATS units of ATC information in support of flight notification, flight coordination, transfer of control, transfer of communication, transfer of surveillance data and transfer of general data. |

# ATN Traffic

## Ground-Ground traffic

With the introduction of AMHS as the replacement for AFTN, a number of AFTN circuit links between centres will need to be upgraded to cater for the increase in traffic load generated by AMHS overheads. Table 4-2 shows a comparison of different size messages transmitted over both an AFTN service and an AMHS service using X.25. From the results shown in Table 4-2 there is an increase in message size of 93% due to overheads generated by AMHS for a typical message of about 250 bytes. As the message size increases the amount of overheads generated becomes less significant to the size of the body of the message. In transitioning from AFTN to AMHS, States will have to anticipate this increase in bandwidth to accommodate AMHS traffic so as to maintain current or better performance of traffic delivery.

It is also important to note that there will also be an increase in other forms of data traffic due to implementation of other ATN applications such as the ATS Inter-facility Data Communication (AIDC) application. AIDC will generally be used by Flight Data Processors (FDP) to communicate between each other, which are normally established in each Fight Information Region (FIR). It can therefore be expected that data generated by this application will increase bandwidth requirements on those links that are required to pass this information between FIRs.

States will need to ensure that not only are the links that are established between States are capable of transferring data in a timely manner but also for those links that provide an alternate path for the applications to use in times of disruption to the primary links.

Table 4-2 Comparison of X.25 Message Sizes Using AFTN and AMHS
(Results courtesy of the INCA Project.)

## Air-Ground Traffic

With the implementation of the air-ground applications it is important to ensure that transit response times are kept to a minimum level so as not to affect the overall response time that it takes for traffic such as ADS reports and CPDLC messages to be delivered to their final destination. This again reflects the need to ensure that critical ground links within the Region are capable of handling this information efficiently.

Another important factor with air-ground traffic is the generation of routing information that is caused by aircraft that will move between various ATN routing domains. To maintain this information in a defined area requires a minimum number of backbone routers to be implemented which protects the majority of all other ATN routers from being flooded with routing information. This information is further explained in Section 5.

# ATN Routing Architecture

The ATN infrastructure can be divided into two main areas to support both the air-ground and ground-ground applications that will operate over the ATN.

For air-ground support the ATN needs to support an ATN Routing Backbone network so that routing information about where an aircraft is can be maintained by this backbone. As aircraft move through various coverage media and FIR boundaries the ATN Routing Backbone will be notified of the changing routing data for each mobile aircraft in the region. The type of ATN Routing Backbone architecture for the Asia Pacific Region is document in the Asia Pacific ATN Routing Architecture Plan (Reference 2) and is summarised in Figure 5-1 of this document.

It is anticipated that the trunks used for the ATN Routing Backbone will also be used to carry ground-ground application data such as the AMHS. This of cause depends upon the routing policies set up between each router, which determine which links are to be used for the different classes of traffic that can be expected to transverse the network.

Figure 5-1 shows the proposed ATN Routing Backbone for the Asia Pacific Region. The ATN Router Backbone tries to use existing trunks that have already been established between the nominated States who will operate the backbone that is currently used for the AFTN. Virtually these trunks will need to be upgraded to cater for the increase in traffic load that will be handled by the ATN. Further details about these trunks are documented in Section 6.

To improve the resilience and redundancy aspects of the ATN routing backbone, it is proposed that additional trunks be incorporated to ensure minimal disruption to the air-ground applications. This effectively ensures that the Asia Pacific Region can function on its own without support from other regions relaying information on behalf of a failed router or trunk service within the Asia Pacific Region. These additional trunks have been shown as dashed lines in Figure 5-1. Also shown are the inter-regional connections between the Asia Pacific Region and its neighbouring Regions. Additional inter-regional connections are also proposed and are further documented in Section 6.

It is important to also note that costs will increase due to implementing higher bandwidth links.  Therefore the region should review its requirements in having to use point to point circuits every where when a number of strategically placed links may suffice with alternate dial up on demand capabilities being deployed between key sites. This may help to offset the costs and still provide for an efficient ground-ground network for the ATN.

Figure 5-1 Proposed Routing Backbone Architecture

# ATN Backbone Trunks

Table 6-3 provides a list of existing or proposed upgrade AFTN circuits that have been selected for the transition to the ATN routing backbone. Also provided in the table are proposed additional new trunks that should be considered to provide the necessary redundancy and backup services for the ATN for the region.

As part of the transition from AFTN to the ATN, the existing link capacity, especially those using X.25, must be able to handle both AFTN and ATN for those States who do not intent to migrate to AMHS straight away. It is assumed that States that have been nominated to provide the ATN backbone routing environment will do so in a timely manner so as to allow those States who are ready to start their implementation programs can do so without too much restriction within the region. Where a nominated State cannot provide the ATN backbone then an alternative arrangement should be put in place for another State, who is willing to provide the service, can do so.

Table 6-3 ATN Circuit Upgrade and Backbone BIS Implementation

| Nominated State | AFTN Current/Proposed Trunks |  | ATN Backbone Connection |  | Target Date Of Implementation |  | Comment |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Speed | Protocol | Speed | Protocol | Circuit | BBIS |  |
| Australia |  |  |  |  |  | 2005 |  |
| Japan (Intra-Regional) | N/A | N/A | 64000bps | X.25 | 2003 |  | New circuit |
| Singapore (Intra-Regional) | 2400bps | COP-B | 64000bps | X.25 | 2003 |  | Upgrade of circuit |
| South Africa (Inter-Regional) | N/A | N/A | 19200bps | X.25 | 2003 |  | New circuit |
| United States (Inter-Regional) | 2400bps | X.25 | 64000bps | X.25 | 2001 |  | Upgrade of circuit |
| China |  |  |  |  |  | 2005 |  |
| Japan (Intra-Regional) | 9600bps | X.25 | 64000bps | X.25 | 2005 |  | Upgrade of circuit |
| Hong Kong, China (Intra-Regional) | 1200bps | None | 64000bps | X.25 | 2005 |  | Upgrade of circuit |
| Pakistan (Inter-Regional) | 2400bps | X.25 | 19200bps | X.25 | 2005 |  | Upgrade of circuit |
| Russian Federation (Inter-Regional) | 2400bps | X.25 | 19200bps | X.25 | 2005 |  | Upgrade of circuit |
| Thailand (Intra-Regional) | N/A | N/A | 64000bps | X.25 | 2002 |  | New circuit |
| Hong Kong, China |  |  |  |  |  | 2002 |  |
| China (Intra-Regional) | 1200bps | None | 64000bps | X.25 | 2005 |  | Upgrade of circuit |
| Japan (Intra-Regional | 9600bps | X.25 | 64000bps | X.25 | 2002 |  | Upgrade of circuit |
| Thailand (Intra-Regional | 2400bps | X.25 | 64000bps | X.25 | 2003 |  | Upgrade of circuit |
| India |  |  |  |  |  | 2005 |  |
| Kenya-Nairobi (Inter-Regional) | 50baud | None | 19200bps | X.25 | 2005 |  | Upgrade of circuit |
| Oman-Muscat (Inter-Regional) | 300baud | None | 19200bps | X.25 | 2005 |  | Upgrade of circuit |
| Singapore (Intra-Regional) | N/A | N/A | 64000bps | X.25 | 2005 |  | New circuit |
| Thailand (Intra-Regional) | 2400bps | X.25 | 64000bps | X.25 | 2003 |  | Upgrade of circuit |
| Japan |  |  |  |  |  | 2002 |  |
| Australia (Intra-Regional) | N/A | N/A | 64000bps | X.25 | 2003 |  | New circuit |
| China (Intra-Regional) | 9600bps | X.25 | 64000bps | X.25 | 2005 |  | Upgrade of circuit |
| Hong Kong, China (Intra-Regional) | 9600bps | X.25 | 64000bps | X.25 | 2002 |  | Upgrade of circuit |
| Europe (Inter-Regional) | N/A | N/A | 64000bps | X.25 | 2005 |  | New circuit |
| Singapore (Intra-Regional) | 9600bps | X.25 | 64000bps | X.25 | 2003 |  | Upgrade of circuit |
| United States (Inter-Regional) | 9600bps | X.25 | 64000bps | X.25 | 2003 |  | Upgrade planned. |
| Singapore |  |  |  |  |  | 2005 |  |
| Australia (Intra-Regional) | 2400bps | COP-B | 64000bps | X.25 | 2003 |  | Upgrade of circuit |
| Bahrain (Inter-Regional) | 2400bps | X.25 | 19200bps | X.25 | 2005 |  | Upgrade of circuit |
| England-London (Inter-Regional) | 1200bps | X.25 | 64000bps | X.25 | 2005 |  | Upgrade of circuit |
| Japan (Intra-Regional) | 9600bps | X.25 | 64000bps | X.25 | 2003 |  | Upgrade of circuit |
| India (Intra-Regional) | N/A | N/A | 64000bps | X.25 | 2005 |  | New circuit |
| Thailand (Intra-Regional) | 1200bps | X.25 | 64000bps | X.25 | 2003 |  | Upgrade of circuit |
| Thailand |  |  |  |  |  | 2002 |  |
| China (Intra-Regional) | N/A | N/A | 64000bps | X.25 | 2002 |  | New circuit |
| Hong Kong, China (Intra-Regional | 2400bps | X.25 | 64000bps | X.25 | 2003 |  | Upgrade of circuit |
| India (Intra-Regional) | 9600bps | X.25 | 64000bps | X.25 | 2003 |  | Upgrade of circuit |
| Italy-Rome (Inter-Regional) | 2400bps | X.25 | 64000bps | X.25 | 2005 |  | Upgrade of circuit |
| Singapore (Intra-Regional) | 1200bps | X.25 | 64000bps | X.25 | 2003 |  | Upgrade of circuit |

# Interconnection of ATN Routers

This section describes the interconnection requirements for all other States ATN routers for the Asia Pacific Region. Figure 7-2 shows a pictorial view of the international interconnection between various Asia Pacific countries. Annex A contains a list of the international connections between countries and proposed bandwidth requirements and implementation dates.

It is proposed that all existing AFTN circuits are upgraded as soon as practicable to use X.25 or other modern protocols that are compatible with the ATN Lower Layers. In doing so, these links would be sized to cater for both AFTN and ATN. This would allow the region to set-up a subnetwork that could support current operational requirements for AFTN and to allow trials and operation services of the ATN to be implemented at minimal cost to the region.

Figure 7-2 Asia Pacific ATN Router Interconnection

# Transition Activities

It is recommended that there will be three stages in the implementation of the ATN infrastructure.

- Stage 1, Upgrade of existing subnetwork infrastructure to support the Backbone BISs (BBISs);

- Stage 2, Implementation of the ATN Regional BBISs; and

- Stage 3, Implementation of supporting ATN BISs.

## Stage 1

This stage consists of upgrading existing AFTN circuits where possible that will support the introduction of the ATN Backbone BISs. Table 6-3 identifies those circuits that will need to be upgraded in both bandwidth and protocols.

In regards to bandwidth requirements, Table 6-3 proposes a preferred speed that will be required when full ATN is implemented. However, lower speeds may be introduced in the initial implementation stages between some locations by bilateral arrangements between States. States will be expected to monitor the performance of these links and increase bandwidth requirements as traffic load increases.

Where new circuits have been identified these will only need to be introduced on a case by case basis as BBISs are implemented.

In respect to the upgrade of protocols, it is recommend that X.25 will be the preferred protocol to be used for the ATN between States in the first instance. However as other more efficient Wide Area Network protocols are implemented in ATN routers such as Frame Relay and Asynchronous Transfer Mode (ATM) it is expected that these protocols will be implemented on a bilateral arrangement between States.

## Stage 2

Stage 2 consists of implementing the Backbone BISs (BBISs) that will support the Asia Pacific Region. The BBISs are important to the success of the ATN implementation program for the region and will need to be reviewed regularly to determine if contingency arrangements should be put in place where nominated States fail to provide the infrastructure in a timely manner.

Table 6-3 provides target dates in which these facilities should be provided.

Note: Implementation of Inter-Regional BBIS connections between Asia Pacific neighbouring regions will also need to be determined and encouraged during this phase.

## Stage 3

Stage 3 is the implementation of all other BISs that will connect to the Backbone BISs.

Table A-4 provides initial target dates for the upgrade of the subnetwork links and protocols and implementation of the BISs for each State. Refinement of the target dates will continue to be updated as States start to develop their implementation programs and can provide feedback to the ATN Transition Task Force.

# Conclusions

The Asia Pacific Region ATN Ground Transition Plan outlines the requirements to increase bandwidth and upgrade protocols for those trunks that will support the main data flow of traffic through the Asia Pacific Region. The plan also provides target dates in which these trunks and implementation of BBISs and BISs will need to occur to ensure a smooth transition of the ATN within the region.

# Recommendations

The members of the APANPIRG/ATNTTF are invited to review and comment on the proposed Asia Pacific Region ATN Ground Transition Plan as presented above.

- ANNEX

# ATN Interconnection Circuits

Table A-4 Asia Pacific BIS Routing Interconnections

| Backbone State | AFTN Current/Proposed Trunks |  | ATN Interconnection |  | Target Date Of Implementation |  | Comment |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Speed | Protocol | Speed | Protocol | Circuit | BIS |  |
| Australia |  |  |  |  |  | 2005 |  |
| Fiji | 2400bps | X.25 | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit required |
| Kiribati | 2400bps | None | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit required |
| New Caledonia | 2400bps | None | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit required |
| Samoa | 50baud | None | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit required |
| Tonga | 50baud | None | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit required |
| Tuvalu | 50baud | None | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit required |
| Wallis Island | 50baud | None | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit required |
| Indonesia | 9600bps | X.25 | 9600bps | X.25 | 2005 | 2005 |  |
| Nauru | 2400bps | X.25 | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit required |
| New Zealand | 2400bps | X.25 | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit required |
| Cook Islands | 2400bps | None | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit required |
| Fiji | 2400bps | X.25 | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit required |
| French Polynesia | 2400bps | X.25 | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit required |
| Niue | 300baud | None | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit required |
| Papua New Guinea | 9600bps | X.25 | 9600bps | X.25 | 2005 | 2005 |  |
| Solomon Islands | 75baud | None | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit required |
| Vanuatu | 300baud | None | 9600bps | X.25 | 2005 | 2005 | New circuit required |
| China |  |  |  |  |  | 2005 |  |
| DPR of Korea | 300baud | None | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit |
| Hong Kong, China | 1200bps | None | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit |
| Macau China | 2400bps | None | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit |
| Mongolia | 1200bps | None | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit |
| Myanmar | 300baud | None | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit |
| Nepal | 300baud | None | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit |
| Republic of Korea | N/A | N/A | 9600bps | X.25 | 2005 | 2005 | New circuit |
| Hong Kong, China |  |  |  |  |  | 2005 |  |
| Taibei | 4800bps | X.25 | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit |
| Macau, China | 2400bps | None | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit |
| Philippines | 300baud | None | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit |
| Viet Nam | 300baud | None | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit |
| India |  |  |  |  |  | 2005 |  |
| Bangladesh | 50baud | None | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit |
| Bhutan | 50baud | None | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit |
| Nepal | 50baud | None | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit |
| Sri Lanka | 2400bps | X.25 | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit |
| Maldives | 2400bps | X.25 | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit |
| Japan |  |  |  |  |  | 2005 |  |
| Republic of Korea | 9600bps | X.25 | 9600bps | X.25 | 2005 | 2005 |  |
| Hong Kong China | 9600bps | X.25 | 9600bps | X.25 | 2005 | 2005 |  |
| Taiwan | 4800bps | X.25 | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit |
| Singapore |  |  |  |  |  | 2005 |  |
| Brunei | 2400bps | X.25 | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit |
| Indonesia | 2400bps | X.25 | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit |
| Malaysia | 1200bps | X.25 | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit |
| Philippines | 2400bps | X.25 | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit |
| Sri Lanka | 2400bps | X.25 | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit |
| Viet Nam | 2400bps | X.25 | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit |
| United States |  |  |  |  |  | 2005 |  |
| American Samoa | 2400bps | X.25 | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit |
| Marshall Islands | 1200bps | X.25 | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit |
| Micronesia | 1200bps | X.25 | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit |
| Palau | 1200bps | X.25 | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit |
| Thailand |  |  |  |  |  | 2005 |  |
| Bangladesh | 300baud | None | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit |
| Cambodia | 300baud | None | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit |
| Laos | 300baud | COP-B | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit |
| Viet Nam | 9600bps | None | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit |
| Malaysia | 2400bps | None | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit |
| Myanmar | 300baud | COP-B | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit |
| Viet Nam | 2400bps | None | 9600bps | X.25 | 2005 | 2005 | Upgrade of circuit |

- ANNEX

# Asia Pacific International AFTN

Figure B-3 Asia Pacific International AFTN

INCA (Investigation of Networked CNS/ATM Applications) project was a joint Airservices Australia and Airsys ATM Pty Ltd ATN research and development program, which investigated the AMHS during 1999/2000.